## Sheet1
Bug description | Status | Assigned to | Raised By | Tested on Version | TestCase Id | Steps to Reproduce | Expected Results | Actual Results | Priority | Severity
Verify "View Product" | New |  | QA Team | 1 | TC-HP-099 | 1. Check footer. | Visible. | Link Missing. | Low | Low
Verify Hover Overlay | New |  | QA Team | 1 | TC-HP-100 | 1. Hover image. | Appears. | No Overlay. | Low | Low
Func: "View Product" | New |  | QA Team | 1 | TC-HP-104 | 1. Click Link. | Redirects. | Link Missing. | Low | Low
Func: Overlay Trans | New |  | QA Team | 1 | TC-HP-105 | 1. Hover in/out. | Smooth. | No Transition. | Low | Low
Func: Add Cart (Over) | New |  | QA Team | 1 | TC-HP-107 | 1. Hover & Click. | Modal opens. | Btn Missing. | High | High
UX: Navbar Vert | New |  | QA Team | 1 | TC-HP-122 | 1. Check alignment. | Aligned. | Misaligned. | Low | Low
UX: Navbar Space | New |  | QA Team | 1 | TC-HP-123 | 1. Check spacing. | Equal. | Uneven. | Low | Low
UX: Grid Align | New |  | QA Team | 1 | TC-HP-124 | 1. Check rows. | Aligned. | Broken. | Medium | Medium
UX: Card Height | New |  | QA Team | 1 | TC-HP-125 | 1. Check heights. | Equal. | Unequal. | Medium | Medium
UX: Navbar Vert Align | New |  | QA Team | 1 | TC-PRD-137 | 1. Check alignment. | Aligned. | Misaligned. | Low | Low
UX: Navbar Spacing | New |  | QA Team | 1 | TC-PRD-138 | 1. Check spacing. | Equal. | Uneven. | Low | Low
UX: Grid Alignment | New |  | QA Team | 1 | TC-PRD-204 | 1. Check rows. | Aligned. | Broken. | Medium | Medium
UX: Card Height | New |  | QA Team | 1 | TC-PRD-205 | 1. Check heights. | Equal. | Unequal. | Medium | Medium
Func: Input 0 | New |  | QA Team | 1 | TC-DET-262 | 1. Type "0". Click Add. | Error Message should appear | Nothing shown... | High | High
Func: Input -1 | New |  | QA Team | 1 | TC-DET-263 | 1. Type "-1". Click Add. | Error Message should appear | Nothing shown... | High | High
UX: Navbar Vert | New |  | QA Team | 1 | TC-DET-327 | 1. Check alignment. | Aligned. | Misaligned. | Low | Low
UX: Navbar Space | New |  | QA Team | 1 | TC-DET-328 | 1. Check spacing. | Equal. | Uneven. | Low | Low
UX: Navbar Vert Align | New |  | QA Team | 1 | TC-LGN-340 | 1. Check vertical alignment... | Perfectly centered. | Misaligned. | Low | Low
UX: Navbar Spacing | New |  | QA Team | 1 | TC-LGN-341 | 1. Check space between... | Equal spacing. | Uneven. | Low | Low
UX: Navbar Vert Align | New |  | QA Team | 1 | TC-CHK-501 | 1. Check vertical alignment. | Perfectly centered. | Misaligned. | Low | Low
UX: Navbar Spacing | New |  | QA Team | 1 | TC-CHK-502 | 1. Check spacing between... | Equal spacing. | Uneven. | Low | Low
UX: Navbar Vert Align | New |  | QA Team | 1 | TC-PAY-558 | 1. Check vertical alignment. | Perfectly centered. | Misaligned. | Low | Low
UX: Navbar Spacing | New |  | QA Team | 1 | TC-PAY-559 | 1. Check spacing between... | Equal spacing. | Uneven. | Low | Low
Verify createAccount... | New |  | QA Team | 1 | TC_9 | 1.Open URL... | HTTP 400 | HTTP 400 not returned | High | High
Verify createAccount... | New |  | QA Team | 1 | TC_10 | 1.Open URL... | HTTP 400 | HTTP 400 not returned | High | High